CRVS e-Death Notification System Rollout

Nyamasheke District

I. Introduction

The Civil Registration and Vital Statistics (CRVS) e-Death Notification System in Western Province started on 15 March 2026.

In Nyamasheke District, the implementation followed the national cascading training model to improve timely and accurate death reporting at the community level.

We expected 588 villages. However, three villages no longer exist. Gasasa and Munini were cleared for tea plantation development, and there are no longer any residents living there. Gafunzo village was also removed because it was considered unsafe, and its residents were relocated to another village.

The training targeted:

- District-level officers

- Cell SEDOs

- Sector Executive Secretaries

- Village leaders

II. Training Implementation in Nyamasheke District

The rollout in Nyamasheke District was conducted over five (5) days:

|  | Expected | Attended | Percentage |
| --- | --- | --- | --- |
| Cell SEDOs | 68 | 68 | 100% |
| Village Leaders | 585 | 583 | 99% |
| CRO | 15 | 11 | 73% |
| District Staff | 2 | 2 | 100% |
| Total | 670 | 664 | 99% |

Number of Village Leaders who attended (In details):

|  | Expected | Attended | Percentage |
| --- | --- | --- | --- |
| Kagano | 50 | 50 | 100% |
| Bushekeri | 32 | 32 | 100% |
| Ruharambuga | 47 | 47 | 100% |
| Karengera | 32 | 32 | 100% |
| Bushenge | 41 | 41 | 100% |
| Shangi | 33 | 32 | 97% |
| Nyabitekeri | 51 | 51 | 100% |
| Kanjongo | 42 | 42 | 100% |
| Rangiro | 23 | 23 | 100% |
| Gihombo | 38 | 37 | 97% |
| Mahembe | 31 | 31 | 100% |
| Kirimbi | 32 | 32 | 100% |
| Macuba | 53 | 53 | 100% |
| Cyato | 34 | 34 | 100% |
| Karambi | 46 | 46 | 100% |
| Total | 585 | 583 | 99% |

The attendance was good at both levels. Most of the invited participants attended the training.

III. Overall Performance in Nyamasheke District

- Most village leaders attended in person.

- All trained participants were enrolled into the e-Death Notification System.

This shows strong commitment from the district leadership to improve civil registration services.

IV. Key Challenges Observed in Nyamasheke District

Although the rollout was successful, some challenges were observed:

- Airtime Constraints for Village Leaders:

The e-Death Notification system uses SMS, which requires village leaders to use their personal airtime. Many village leaders do not have enough airtime to regularly report deaths.

- Difficulty for Some Elderly Participants in Using the System:

Some elderly participants found it difficult to use the system due to limited digital skills. In some cases, they relied on their children or other family members, using their devices and phone numbers, which may affect proper ownership and accountability in the system.

- Limited SIM Card Compatibility:

Another challenge observed is that the system currently works only with MTN SIM cards. Village leaders who use other mobile networks are required to have an MTN SIM card in order to send notifications. This creates inconvenience and may delay reporting for those who do not have or regularly use MTN lines.

Another issue is that some village leaders use old phones. These phones may not support the system properly, which can make it difficult to send notifications on time.

V. Recommendations

To improve future rollout activities:

- Continuous Follow-Up and Support

District teams should provide regular follow-up and technical support.

VI. Conclusion

The rollout of the CRVS e-Death Notification System in Nyamasheke District was successfully implemented between 15 March and 22 March 2026.

Attendance was high, and most participants were trained and enrolled in the system. However, the airtime issue and some operational challenges need to be addressed to ensure sustainability.

Nyamasheke District is ready to implement the e-Death Notification System and improve timely and accurate death registration services.